## Read me
NSM SOURCING · PROCUREMENT TEMPLATE NSM-03
Stakeholder Map and RACI
Purpose | Identifies the stakeholders of a purchase, classifies them by influence and interest, and fixes who does, approves, advises on and is told about each step.
Step 1 | List stakeholders and score influence and interest from 1 to 5. The approach is calculated.
Step 2 | On the RACI sheet, rename the role columns if needed and adjust the letters. Each activity must have exactly one A.
Step 3 | Agree the RACI at the start of the project and attach it to the procurement strategy (template 06).
Sheet: Stakeholder map | Influence and interest grid with engagement plan.
Sheet: RACI | Roles for each step of the procurement cycle.
Legend | Yellow cells are inputs. White cells with dark text are calculated by formula; do not overwrite them. The first filled row is an example: replace or delete it.
Practitioner note | The people who will use the product are the best source of the real need. Bringing production planning, quality and finance into one cross-functional team early prevents late changes to the specification and makes the award decision easier to approve.
NSM Sourcing · nsmsourcing.com · Licensed under CC BY 4.0: free to use and adapt with credit to NSM Sourcing. General guidance, not legal advice. Terminology follows the CIPS Procurement and Supply Cycle; this is an independent work, not endorsed by CIPS.

## Stakeholder map
NSM SOURCING · PROCUREMENT TEMPLATE NSM-03
Stakeholder Map
Who is affected by the purchase, how much they can influence it and how we will involve them.
Stakeholder (name or role) | Department | Influence (1 to 5) | Interest (1 to 5) | Approach (calculated) | Main concerns and requirements | How we will engage | Owner | Frequency
Production planning manager | Operations | 4 | 5 | Manage closely | Supply continuity, lead times | Member of the sourcing team; weekly review
Quality manager | Quality | 4 | 4 | Manage closely | Supplier qualification, audits | Joint supplier audits; signs off qualification
Finance director | Finance | 5 | 2 | Keep satisfied | Budget, payment terms, cash flow | Approves strategy and award; monthly summary

## RACI
NSM SOURCING · PROCUREMENT TEMPLATE NSM-03
Responsibility Assignment Matrix (RACI)
R: responsible (does the work) A: accountable (one per activity) C: consulted I: informed
Activity | Requester | Budget holder | Procurement | Technical | Quality | Finance | Legal | Check (one A)
Define need and specification | R | C | C | A | C | I |  | OK
Pre-tender estimate | C | I | R | A |  | C |  | OK
Procurement strategy | C | A | R | C | C | C | I | OK
Market engagement and RFI | I | I | A | C |  |  |  | OK
Supplier pre-qualification and audit | I |  | A | C | R | C |  | OK
Tender documents | C | I | A | R | C | C | C | OK
Technical evaluation | C |  | C | A | C |  |  | OK
Commercial evaluation |  | I | A | C |  | C |  | OK
Negotiation |  | C | A | C |  | C | C | OK
Award approval | I | A | R | C |  | C |  | OK
Contract signature |  | A | R |  |  | C | C | OK
Receiving inspection | C |  | I | C | A |  |  | OK
Supplier performance review | C | I | A | C | R |  |  | OK