## Read me
NSM SOURCING · PROCUREMENT TEMPLATE NSM-07
Procurement Plan Register
Purpose | Turns individual requisitions and project needs into a planned pipeline, so that lead times are respected and the procurement team can plan its workload.
Step 1 | Add one row per requirement or package. Use template 06 headings for the positioning and route.
Step 2 | Plan dates backwards from the date the goods or services are needed, allowing for supplier lead time.
Step 3 | Update the status weekly. The Summary sheet totals count and value by status and by route.
Sheet: Plan | One row per planned procurement, with filters.
Sheet: Summary | Counts and values by status and route; average cycle time.
Legend | Yellow cells are inputs. White cells with dark text are calculated by formula; do not overwrite them. The first filled row is an example: replace or delete it.
Practitioner note | A plan linked to the production or project plan is what turns ad hoc purchasing into a supply base. When raw material demand is planned and tracked with production planning, contracts and bulk orders become possible and suppliers have a reason to offer better terms.
NSM Sourcing · nsmsourcing.com · Licensed under CC BY 4.0: free to use and adapt with credit to NSM Sourcing. General guidance, not legal advice. Terminology follows the CIPS Procurement and Supply Cycle; this is an independent work, not endorsed by CIPS.

## Plan
NSM SOURCING · PROCUREMENT TEMPLATE NSM-07
Procurement Plan Register
The pipeline of planned procurements for a project or a year: value, route, key dates and status.
ID | Requirement | Category | Business owner | Estimated value | Curr. | Positioning | Route to market | Strategy approved | RFx issued | Bids due | Award | Contract start | Contract end | Cycle days | Status | Procurement lead | Notes and dependencies | Regulatory flags (CBAM, sanctions, forced labour, AI) | Continuity critical
P01 | Switchgear panels for substations | Electrical equipment | Grid operations | 850000 | EUR | Leverage | Two-stage tender | 2026-11-02 | 2026-12-01 | 2027-01-15 | 2027-02-15 | 2027-03-01 | 2029-02-28 | 119 | Strategy

## Summary
NSM SOURCING · PROCUREMENT TEMPLATE NSM-07
Pipeline summary
Values are added without currency conversion; use one currency per register or convert before entry.
Status | Count | Estimated value
Not started | 0 | 0
Strategy | 1 | 850000
In market | 0 | 0
Evaluation | 0 | 0
Awarded | 0 | 0
Contracted | 0 | 0
On hold | 0 | 0
Cancelled | 0 | 0
Total | 1 | 850000
Route to market | Count | Estimated value
RFQ | 0 | 0
Single-stage tender | 0 | 0
Two-stage tender | 1 | 850000
Reverse auction | 0 | 0
Framework call-off | 0 | 0
Single source | 0 | 0
Average cycle days (strategy to contract start) | 119